## Product Backlog
Project Name | OpenCart (Frontend)
Client | OpenCart
Created By | Name of the Product Owner
Creation Date | DD-MM-YYYY
Approval Date | DD-MM-YYYY
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
OpenCart_Epic_001 : For a new e-commerce website to launch, the highest Business Value will be when a new user is able to buy an item from the website. | US001 | Registration | As a First-time visitor to the e-commerce website, I want to register my account, So that I can login to application. | New | New user should able to Register account with valid data.
| US002 | Login | As a registered user, I want to login to the website, So that I can see my account details etc.. | New | System must validate user credentials and allow login if credentials are correct..
| US003 | Logout | As a registered user, I want to logout from website, So that no one else can't access my account. | New | System must logout after login.
| US004 | User search products | As a user, I want to be able to search items, So that I can add them to cart and do payment. | New | User should able to search products and add them to cart.

## Sprint Planning
Project Name | OpenCart (Frontend)
Client | OpenCart
Created By | Name of the Scrum Master
Attendees | Scrum Team
Creation Date | DD-MM-YYYY
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
OpenCart_Epic_001 : For a new e-commerce website to launch, the highest Business Value will be when a new user is able to buy an item from the website. | US001 | Registration | As a First-time visitor to the e-commerce website, I want to register my account, So that I can login to application. | 8 | 1
| US002 | Login | As a registered user, I want to login to the website, So that I can see my account details etc.. | 5 | 1
| US003 | Logout | As a registered user, I want to logout from website, So that no one else can't access my account. | 3 | 1
| US004 | User search products | As a user, I want to be able to search items, So that I can add them to cart and do payment. | 5 | 3
Story Points | Hours
1 | 1 Hour/ Day (Depends on company)
0,1, 1, 2, 3, 5, 8 | Fibinacci series

## Tasks
Developer Tasks | QA Tasks
Under standing Requirements | Under standing Requirements
Desing | Writing Test Scenarios
Coding | Writing Test Cases
Unit Testing | Test Case Reviews
Integration Testing | Test Data Preparation
Code Review | Test Environment Setup
Bug Fixes | Test Execution
Team Meetings | Re-Testing Bugs
Any other... | Team Meetings
Automation
Any other…