## Product Backlog
Project | Dealmart.com
Stake holders /Customers/users | abc, xyz etc..
Created By | Name of the Product Owner
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
For a new e-commerce website to launch, the highest Business Value will be when a new user is able to buy an item from the website. | US001 | First time visitor can make the payment as a guest user without having to register | As a First-time visitor to the e-commerce website, I want to be able to buy a listed product, So that I can use the product I buy. | New
| US002 | New user can register on the website | As a First time visitor to the website, I want to be able to register on the website, So that I can browse and buy listed products from the website. | New
| US003 | Registered User can Browse items listed | As a Registered Website User, I want to be able to browse listed products from the website, So that I can make my choice and buy a listed product from the website. | New
| US004 | Registered User can add items to the cart | As a Registered Website User, I want to be able to add items to the cart, So that I can buy a listed product from the website. | New
| US005 | Registered User can make payment for the items added to the cart. | As a Registered Website User, I want to be able to buy listed products, So that I can use the product I buy. | New

## Sprint Planning
Project | Dealmart.com
Srum Team | Dev, QA, PO, Scrum master, DecOps etc..
Created By | Name of the Product Owner
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
For a new e-commerce website to launch, the highest Business Value will be when a new user is able to buy an item from the website. | US001 | First time visitor can make the payment as a guest user without having to register | As a First-time visitor to the e-commerce website, I want to be able to buy a listed product, So that I can use the product I buy. | 8 | 1
| US002 | New user can register on the website | As a First time visitor to the website, I want to be able to register on the website, So that I can browse and buy listed products from the website. | 3 | 1
| US003 | Registered User can Browse items listed | As a Registered Website User, I want to be able to browse listed products from the website, So that I can make my choice and buy a listed product from the website. | 5 | 2
| US004 | Registered User can add items to the cart | As a Registered Website User, I want to be able to add items to the cart, So that I can buy a listed product from the website. | 5 | 3
| US005 | Registered User can make payment for the items added to the cart. | As a Registered Website User, I want to be able to buy listed products, So that I can use the product I buy. | 8 | 3

## Test Cases
TCID | User Story ID | Feature/Title | User Story | Steps | Expected
TC_DEALM_001 | US001 | First time visitor can make the payment as a guest user without having to register | As a First-time visitor to the e-commerce website, I want to be able to buy a listed product, So that I can use the product I buy. | 1) Open Application URL 2) Got to catalog page 3) List a product 4) Add to cart 5) Select payment method 6) Complete payment | User is able to list and buy the product
TC_DEALM_002 | US002 | New user can register on the website | As a First time visitor to the website, I want to be able to register on the website, So that I can browse and buy listed products from the website. | 1) Open Application URL 2) Click on Register link 3) Pride user details 4) Click on Submit | New user should able to register to website